DairyDirect

3-Day Demo Prototype Roadmap

What to build, what to skip, and how to survive the weekend

Version 1.0  |  April 2026  |  Internal Use Only

| Demo Date | Day 3 End — April 12, 2026 |
| --- | --- |
| Stack | Node.js + Express + PostgreSQL + React (Web UI) |
| Goal | Functional clickable demo — not production code |
| Who presents | Developer / PM to stakeholders |
| Scope motto | Show the flow. Hide the plumbing. |

DEMO SCOPE ONLY — Not for production deployment

# DEMO STRATEGY & GROUND RULES

You have 72 hours. A demo prototype is NOT a production app — it is a story told through a working interface. Your only job is to make the core user journey work end-to-end without crashing in front of stakeholders.

## What a Good Demo Proves

- Customer can register and log in (OTP or mock OTP)

- Products are visible — Milk, Paneer, Ghee, Buttermilk

- Customer can place a one-time order

- Customer can create a milk subscription (weekly/monthly)

- Admin can see all orders on a dashboard

- Order status can be updated (simulated delivery flow)

- Quality report can be filed by customer

## What to CUT for Demo (Do NOT build these)

| Feature | Why Cut for Demo | Show Instead |
| --- | --- | --- |
| Real OTP via MSG91 | Setup & cost overhead | Hardcode OTP as 123456 for any number |
| Razorpay real payment | Live keys + webhook setup = hours | Mock payment: button says 'Pay' → order confirmed |
| Live GPS tracking | Needs delivery app + WebSocket server | Static map with a moving pin on a timer (fake) |
| FCM Push Notifications | App registration + Firebase setup | Show a toast/banner inside the web UI instead |
| PDF Invoice generation | Nice-to-have | Show order summary screen instead |
| Delivery Personnel App | Separate Flutter app = 2 days alone | Admin dashboard with a status-update button |
| Image upload to S3 | AWS setup time | Use placeholder/static images from Unsplash URL |
| Forgot Password / Account settings | Not part of core flow | Skip entirely |
| Subscription Pause/Resume | Edge case feature | Mention in demo script as 'available in full version' |

## Demo Stack Decision (3-Day Optimised)

Use a React web app as the frontend — not Flutter. Building Flutter + backend in 3 days is too risky. A responsive React web app looks identical in a demo and is 3x faster to build.

| Layer | Choice | Why for Demo |
| --- | --- | --- |
| Backend | Node.js + Express | Fastest REST API setup you know |
| Database | PostgreSQL + Prisma | Real DB from day 1 — not mocked. Impressive in demo. |
| Frontend | React + Vite + Tailwind CSS | Fast, looks sharp, no Flutter setup delay |
| Auth | Phone + hardcoded OTP (123456) | Zero SMS cost, instant setup |
| Payment | Mock (button click = success) | Demos the flow without real money |
| Maps | Google Maps JS embed (static) | API key in 5 min, fake moving pin via setInterval |
| Hosting | localhost / ngrok | ngrok gives a shareable URL in 2 minutes for demo day |

# DAY 1 — BACKEND + DATABASE

Goal by end of Day 1: Running API server with auth, products, and orders working. Testable via Postman. Database seeded with demo data.

## Day 1 Hour-by-Hour Plan

| Time Slot | Task | Owner | Priority |
| --- | --- | --- | --- |
| 9:00–10:00 | Project setup: Node.js + Express + Prisma init. Create GitHub repo. Docker Compose with PostgreSQL. | Backend Dev | MUST DO |
| 10:00–11:00 | Write Prisma schema: users, products, product_variants, orders, order_items, subscriptions tables. | Backend Dev | MUST DO |
| 11:00–11:30 | Run prisma migrate dev. Seed script: 4 products (Milk variants, Paneer, Ghee, Buttermilk) with placeholder image URLs. | Backend Dev | MUST DO |
| 11:30–12:30 | Auth Module: POST /auth/otp/send (log to console), POST /auth/otp/verify (accept 123456 for any number). Return JWT. | Backend Dev | MUST DO |
| 12:30–13:30 | LUNCH BREAK — protect this time | — | MUST DO |
| 13:30–14:30 | User profile: GET /me, POST /users/address. JWT middleware protecting all non-auth routes. | Backend Dev | MUST DO |
| 14:30–16:00 | Product Module: GET /products (with category filter), GET /products/:id. Returns variants. Admin: POST /products (no image upload yet). | Backend Dev | MUST DO |
| 16:00–17:30 | Order Module: POST /orders (create from cart), GET /orders (mine), GET /orders/:id, PATCH /orders/:id/status (admin). | Backend Dev | MUST DO |
| 17:30–18:30 | Subscription Module: POST /subscriptions, GET /subscriptions/me, PATCH /subscriptions/:id/cancel. | Backend Dev | MUST DO |
| 18:30–19:00 | Quality Report: POST /reports (linked to order), GET /reports (admin). | Backend Dev | MUST DO |
| 19:00–20:00 | Smoke test ALL endpoints in Postman. Fix any 500 errors. Export Postman collection. | Backend Dev | MUST DO |
| 20:00–21:00 | Admin endpoints: GET /admin/orders (all orders + filter), GET /admin/subscriptions, GET /admin/reports. Basic stats endpoint. | Backend Dev | DO IF TIME |

### Day 1 Deliverable Checklist

| # | Deliverable | Check |
| --- | --- | --- |
| 1 | API server running on localhost:3000 | [ ] |
| 2 | PostgreSQL connected, all tables created | [ ] |
| 3 | 4 products seeded (Milk 500ml/1L, Paneer, Ghee, Buttermilk) | [ ] |
| 4 | POST /auth/otp/verify returns JWT for OTP 123456 | [ ] |
| 5 | POST /orders creates an order, returns order ID | [ ] |
| 6 | POST /subscriptions creates a subscription | [ ] |
| 7 | POST /reports creates a quality report | [ ] |
| 8 | Postman collection with all endpoints saved | [ ] |

### Day 1 — Key Database Schema (Quick Reference)

users          : id, phone, name, role (CUSTOMER/ADMIN), created_at

addresses      : id, user_id, street, city, pincode, lat, lng

products       : id, name, category, price, image_url, is_active

product_variants: id, product_id, label (500ml/1L/500g), price

orders         : id, user_id, type (SINGLE/SUBSCRIPTION), status, total, address_id

order_items    : id, order_id, product_id, variant_id, qty, unit_price

subscriptions  : id, user_id, variant_id, qty, frequency, start_date, status

quality_reports: id, order_id, user_id, issue_type, description, status

End-of-Day-1 Test: Open Postman. Register a user, place an order, create a subscription, file a quality report — all without errors. If this works, Day 2 is frontend. If not, fix tonight.

# DAY 2 — FRONTEND: CUSTOMER APP + ADMIN PANEL

Goal by end of Day 2: A React web app where a customer can register, browse products, place an order, subscribe to milk. Admin can view all orders and update status. Runs on localhost.

## Day 2 Hour-by-Hour Plan

| Time Slot | Task | Owner | Priority |
| --- | --- | --- | --- |
| 9:00–9:30 | Vite + React + Tailwind CSS setup. Create folder structure: /customer and /admin routes. React Router v6. | Frontend Dev | MUST DO |
| 9:30–10:30 | Customer: Login screen — phone input + OTP box (OTP auto-fills 123456 in dev mode). Calls /auth/otp/* APIs. Stores JWT in localStorage. | Frontend Dev | MUST DO |
| 10:30–12:00 | Customer: Home screen + Product Catalogue. Grid of 4 products with image, name, price. Category filter tabs (All/Milk/Paneer/Ghee/Buttermilk). | Frontend Dev | MUST DO |
| 12:00–13:00 | Customer: Product detail page. Variant selector (500ml / 1L). 'Add to Cart' button. Cart sidebar or cart page. | Frontend Dev | MUST DO |
| 13:00–14:00 | LUNCH BREAK | — | MUST DO |
| 14:00–15:30 | Customer: Checkout screen. Address form. Mock payment button 'Pay ₹XXX' → POST /orders → show Order Confirmed screen with order ID. | Frontend Dev | MUST DO |
| 15:30–16:30 | Customer: Subscription screen. Choose Milk variant, qty, frequency (Weekly/Monthly), start date. POST /subscriptions. Show success. | Frontend Dev | MUST DO |
| 16:30–17:00 | Customer: My Orders page. List of orders with status badge (Pending/Confirmed/Delivered). Click order → order detail view. | Frontend Dev | MUST DO |
| 17:00–17:30 | Customer: Quality Report screen. Dropdown for issue type, text description, submit. Tied to a specific order. | Frontend Dev | MUST DO |
| 17:30–18:30 | Admin: Login (admin phone + OTP). Admin Dashboard home: 4 stat cards — Total Orders, Active Subscriptions, Pending Complaints, Revenue. | Frontend Dev | MUST DO |
| 18:30–19:30 | Admin: Orders table — all orders with user name, total, status. Dropdown to change status (Confirmed/Out for Delivery/Delivered). | Frontend Dev | MUST DO |
| 19:30–20:00 | Admin: Subscriptions list table. Complaints table with status. | Frontend Dev | MUST DO |
| 20:00–21:00 | Wire up fake 'Live Tracking' screen: Google Maps embed with a hardcoded delivery pin. Add JS setInterval to move pin slightly over 30s. | Frontend Dev | DO IF TIME |

## Day 2 — Screen Map

| Role | Screen | Route | API Used |
| --- | --- | --- | --- |
| Customer | Login / OTP | /login | POST /auth/otp/send, /auth/otp/verify |
| Customer | Home / Product List | / | GET /products |
| Customer | Product Detail | / product/:id | GET /products/:id |
| Customer | Cart + Checkout | /checkout | POST /orders |
| Customer | Order Confirmed | /order/:id | GET /orders/:id |
| Customer | My Orders | /orders | GET /orders |
| Customer | Subscription | /subscribe | POST /subscriptions |
| Customer | Live Tracking (fake) | /track/:id | Static map + timer |
| Customer | Quality Report | /report | POST /reports |
| Admin | Login | /admin/login | POST /auth/otp/verify |
| Admin | Dashboard | /admin | GET /admin/stats |
| Admin | Orders | /admin/orders | GET /admin/orders, PATCH /orders/:id/status |
| Admin | Subscriptions | /admin/subscriptions | GET /admin/subscriptions |
| Admin | Complaints | /admin/reports | GET /admin/reports |

### Day 2 Deliverable Checklist

| # | Deliverable | Check |
| --- | --- | --- |
| 1 | Customer can login with phone + OTP 123456 | [ ] |
| 2 | Product catalogue loads with all 4 product types | [ ] |
| 3 | Customer can add to cart and reach checkout | [ ] |
| 4 | Clicking 'Pay' creates a real order in the database | [ ] |
| 5 | Customer can create a milk subscription | [ ] |
| 6 | Customer can file a quality report | [ ] |
| 7 | Admin can login and see dashboard stats | [ ] |
| 8 | Admin can change order status from dashboard | [ ] |

### Pro Tips for Day 2

- Use Tailwind utility classes only — no custom CSS files. Speed matters.

- Use a free UI component kit: shadcn/ui or Flowbite React — pre-built cards, tables, buttons.

- Hardcode Ahmedabad map coordinates for the fake tracking screen.

- Use https://source.unsplash.com as image URLs for products in seed data — instant photos.

- Show skeleton loaders (Tailwind animate-pulse) — makes the app feel real even if APIs are slow.

End-of-Day-2 Test: Open the app in a browser. Walk through the full customer journey (login → browse → order → subscribe → report) without touching Postman. If it flows, Day 3 is polish + demo prep.

# DAY 3 — POLISH, DEMO PREP & DELIVERY

Goal by end of Day 3: Demo-ready app. No crashes during the walkthrough. Seed data looks realistic. You have a demo script. ngrok is running. Backup plan ready.

## Day 3 Hour-by-Hour Plan

| Time Slot | Task | Owner | Priority |
| --- | --- | --- | --- |
| 9:00–10:30 | Bug fixing pass: Walk through every screen top-to-bottom. Fix any broken API calls, blank screens, or form errors. Log nothing new — only fix. | Full Dev | MUST DO |
| 10:30–11:30 | Seed realistic demo data: 3 customer accounts, 2 admin accounts, 8 orders in various statuses, 3 active subscriptions, 2 quality reports. | Backend Dev | MUST DO |
| 11:30–12:30 | UI polish: Consistent colours, readable fonts, no broken layouts on 1366x768 screen (projector resolution). Fix padding, add loading states. | Frontend Dev | MUST DO |
| 12:30–13:30 | LUNCH BREAK | — | MUST DO |
| 13:30–14:00 | Set up ngrok: ngrok http 3000. Note the public URL. Test full flow on the ngrok URL (simulates real-world access). Share URL for remote audience. | DevOps | MUST DO |
| 14:00–14:30 | Demo script dry run #1: Walk through all 4 demo scenarios (listed below). Time yourself. Target: under 8 minutes total. | PM / Dev | MUST DO |
| 14:30–15:30 | Add any missing visual proof points: order confirmation number, subscription active badge, complaint status badge, admin revenue counter. | Frontend Dev | MUST DO |
| 15:30–16:00 | Demo script dry run #2: Have someone else click while you narrate. Catch any UX confusion. | PM / Dev | MUST DO |
| 16:00–17:00 | Fake tracking screen polish: Map loads, delivery pin appears, moves slightly over 30 seconds, shows 'Delivered' toast. Rehearse this separately. | Frontend Dev | DO IF TIME |
| 17:00–18:00 | Write a 1-page 'What's Next' slide or doc: Phase 1 features not in demo (real OTP, real payment, Flutter app, etc.). Shows vision beyond demo. | PM | DO IF TIME |
| 18:00–19:00 | Full dress rehearsal: Complete demo from scratch on a clean browser (incognito). Simulate stakeholder questions. | Full Team | MUST DO |
| 19:00–19:30 | Freeze all code changes. No new features after this point. Only critical crash fixes allowed. | Lead Dev | MUST DO |
| 19:30+ | Rest. The demo is ready. | Everyone | MUST DO |

## The 4 Demo Scenarios (Your Script)

Each scenario should take ~2 minutes max. Practice transitions between them. Have a 'reset' seed script ready to restore demo data if something goes wrong.

| # | Scenario | Screens to Show | Key Talking Point |
| --- | --- | --- | --- |
| 1 | New Customer Onboarding & Browse | Login → Home → Product List → Product Detail | 'Any local customer can sign up in 30 seconds and see our full product range.' |
| 2 | Placing an Order (One-Time) | Cart → Checkout → Pay → Order Confirmed → My Orders | 'The entire purchase flow — from cart to confirmation — is seamless. No calls needed.' |
| 3 | Milk Subscription | Subscribe page → Choose plan → Confirm → My Subscriptions tab | 'Weekly or monthly plans. Customers set it once. We deliver automatically every day.' |
| 4 | Admin Operations | Admin Login → Dashboard → Orders → Change status → Complaints | 'Operations team sees everything live. One click to update order status or resolve a complaint.' |

## Demo Day Checklist

| # | Item | Status |
| --- | --- | --- |
| 1 | Backend server running (node index.js or pm2 start) | [ ] |
| 2 | React dev server running (npm run dev) | [ ] |
| 3 | ngrok tunnel active, URL tested | [ ] |
| 4 | Demo seed data loaded (realistic names, orders, subscriptions) | [ ] |
| 5 | Google Maps API key working in tracking screen | [ ] |
| 6 | Tested on projector/external screen resolution (1366x768 or 1920x1080) | [ ] |
| 7 | Incognito browser tab ready with app URL | [ ] |
| 8 | Backup: Postman collection as fallback if UI crashes | [ ] |
| 9 | Phone screen record as backup video if live demo fails | [ ] |
| 10 | 'What's Next' slide/doc ready for Q&A | [ ] |

## If Something Breaks — Fallback Plan

| Problem | Fallback |
| --- | --- |
| Backend API crashes | Use Postman to demonstrate API responses directly — show JSON, explain the flow verbally. |
| UI blank screen | Switch to admin panel which is simpler and more stable. Show backend data in Postman. |
| Database corrupted | Re-run seed script: npx prisma migrate reset --force && node seed.js (< 60 seconds). |
| ngrok disconnects | Switch to localhost demo if stakeholders are in-person. For remote: restart ngrok, new URL. |
| Maps not loading | Show a screenshot of the tracking screen instead. Explain: 'Live map uses Google Maps API.' |

# 3-DAY SUMMARY AT A GLANCE

| Day | Focus | End State | Risk |
| --- | --- | --- | --- |
| Day 1 (Backend) | Node.js + Express + PostgreSQL + Prisma. All core APIs: auth, products, orders, subscriptions, quality reports. | Complete REST API testable in Postman. Database seeded. | LOW — backend is straightforward if schema is clear from Day 1 morning. |
| Day 2 (Frontend) | React + Vite + Tailwind. Customer app: login, catalogue, cart, checkout, subscription, quality report. Admin panel: dashboard, orders, complaints. | Full web app running locally. Both customer and admin journeys work end-to-end. | MEDIUM — most time spent here. Cut fake tracking if behind. |
| Day 3 (Polish) | Bug fixing, realistic seed data, ngrok setup, demo script, 2x dry run rehearsals, code freeze. | Demo-ready. Runs without crashing. 4 scenarios rehearsed. Fallback plan in place. | LOW if Day 2 was solid. HIGH if Day 2 was unfinished. |

## Feature Scope — Final Word

| Feature | In Demo? | Notes |
| --- | --- | --- |
| Product Catalogue (4 products) | YES — Full | Milk, Paneer, Ghee, Buttermilk |
| Customer Login (OTP) | YES — Mocked | OTP = 123456 for any phone |
| One-Time Purchase Flow | YES — Full | Real order created in DB |
| Milk Subscription | YES — Full | Real subscription record created |
| Quality Report | YES — Full | Tied to real order |
| Admin Dashboard | YES — Basic | Stats + order management |
| Order Status Updates | YES — Full | Admin changes status in UI |
| Live Delivery Tracking | YES — Faked | Moving pin on Google Maps with timer |
| Real OTP (MSG91) | NO | Phase 1 production feature |
| Real Payment (Razorpay) | NO | Mock button — Phase 1 feature |
| Delivery Personnel App | NO | Phase 1 — Flutter app |
| Push Notifications | NO | Phase 1 — FCM integration |
| Subscription Pause/Resume | NO | Phase 1 edge-case feature |
| PDF Invoices | NO | Phase 1 — nice-to-have |

Remember: A demo prototype is judged on clarity of vision and stability of the core flow — not on completeness. Show less, show it perfectly, and explain the roadmap for the rest. That is how you win stakeholder confidence.

## Useful Commands Cheat Sheet

# Backend

npm install && npx prisma migrate dev && node seed.js

node index.js   # or: npx nodemon index.js

# Frontend

npm create vite@latest client -- --template react

cd client && npm install && npm install -D tailwindcss postcss autoprefixer

npx tailwindcss init -p && npm run dev

# Database reset (if seed data corrupted)

npx prisma migrate reset --force && node seed.js

# Expose to internet for demo

ngrok http 3000          # backend

ngrok http 5173          # or expose frontend directly

# Quick DB inspection

npx prisma studio        # opens DB browser at localhost:5555